## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Physics engine does't work | 13 | 100 | 1300 | 2023-03-24 |  | A | Accepted as a possibility but I won't let it impede progress. I will follow the testing cutting outline and attempt to Resolve this ASAP
ITC doesn't work as expected | 20 | 40 | 800 | 2023-03-24
I don't have enough time to work on project and I fall behind | 8 | 70 | 560 | 2023-03-24 | Mitigated | M | More precise time-management will be employed and weekly checkins will keep me accountable
Time estimates are lower than the time spent | 70 | 8 | 560 | 2023-03-24 | Mitigated | M | I increase time estimate values and adjust schedule accordingly. RTOS > partying
Graphics take too long to create | 40 | 13 | 520 | 2023-03-24
I require over 100% CPU util to accomplish goals | 2 | 70 | 140 | 2023-03-24
Physics engine take too long to debug | 3 | 20 | 60 | 2023-03-24
Data structures don't hold data / perform as expected | 20 | 20 | 400 | 2023-03-24
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100